## Sheet1
| Project initialization Stage | Project Start Phase | Project Steady Phase |  |  |  | Project Termination Phase
| PR0 | PR1 | PR2 | PR3 | PR4 | PR5 |  | Presentation
| 2016-10-25 | 2016-11-01 | 2016-11-08 | 2016-11-15 | 2016-11-22 | 2016-11-29 | 2016-12-06 | 2016-12-13
Due: | 1) environment setup (git, .net communication) 2) high-level requirement 3) Discuss System architecture 4) Lock requirements | 1) Verify architect will work by writing core pieces 2) Use case diagrams + scrapbook of what the screens will look like 3) research how to upload files, where it will live 4) Create master page template (REST, MVC) 5) setup GIT Repo | 1) a few pages are designed - something working with database (when submite pgram, db stores path) 2) SignalR | 1) most pages fully working | 1) All "must have" completed 2) work on "can have" | 1) complete "can have" 2) any program diagrams | 1) Final Documentation 2) presentation preparation 3) code wrap-up